## issues
Issue | Title | Caterogory | Hardware | OS | Detail | Comments | Priority | Mile Stone
1 | 1366x768 60 Hz | Resolution Support | ??? | ??? | Current Mode Displays 1360x768 60 Hz instead of of 1366x768 60 Hz a. Please modify any reference of 1366x768 from the code to 1360x768. b. Now Recommended Mode should be changed to 1280x1024 60 Hz from 1366x768 60 Hz. c. When 1360x768 60 Hz is selected on the Server / Laptop, LCD8500 OSD should show Current Mode as 1360x768 60 Hz instead of 1366x768 60 Hz | Need clarfication | P1
2 | 1152x870 70 Hz | Resolution Support | HP Proliant DL380 & DL360 Gen 9 Server : Direct : | RHEL_7.2_x86_64 | 1.Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2.LCD8500 OSD displays “1152x870 70 Hz”. This is an unsupported resolution as per the LCD8500 specs. Need to talk to HP Note: Login Screen | customer need to revert back | P3
3 | 1024x768 60 Hz | Resolution Support | HP Proliant DL380 and DL360 Gen 9 Server : Raven / Redbird / Blackbird : | RHEL_7.2_x86_64 | 1. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. When LCD8500 is directly connected to the server , there is no issue. | Check Point 9, detection is ok but its not fit to panel | P1
4 | 1280x800 60 Hz | Resolution Support | HP Proliant DL380 & DL360 Gen 9 Server : Raven / Redbird / Direct : | RHEL_7.2_x86_64 | 1. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. LCD8500 OSD displays “1024x768 60 Hz” instead of “1280x800 60 Hz “. 3. Bottom Status bar is not visible. |  | P1
5 | 1440x900 60 Hz | Resolution Support | HP Proliant DL380 and DL360 Gen 9 Server : Raven / Redbird / Blackbird / Direct : | RHEL_7.2_x86_64 | 1. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. LCD8500 OSD displays “1152x870 60 Hz” instead of “1440x900 60 Hz “. Bottom Status bar is not visible |  | P1
6 | 800x600 60 Hz | Resolution Support | HP Proliant DL380 Gen 7 Server : Raven / Redbird / Direct : | Windows Server 2K8 R2 | 1. LCD8500 OSD displays “1024x768 60 Hz” instead of “800x600 60 Hz “. 2. Snapshots : NOTE : This is a known Issue. Cannot be fixed. Hardware detection of the resolution itself is 1024 x 768 . | H/W Limitation | P3
7 | 1680x1050 60Hz | Resolution Support | HP Proliant DL360 Gen 7 Server : Raven : | SLES_11_x86_64 | 1. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. LCD8500 OSD displays “1680x1050 60 Hz”. 3. This issue is seen once. | Hard to duplicate | P3
8 | 1024x768 75 Hz | Image Adjustment(Auto Adjust Algorthirm) | HP Proliant DL360 Gen 7 Server : Raven : | SLES_11_x86_64 | 1. There is an 2mm (approximately ) cut ( Blank Screen ) shown on the right side. This is intermittent. 2. Autoconfiguration does not align it always. 3. 1024x768 60 Hz works fine. |  | P2
9 | 1024x768 60 Hz | Image Adjustment(Auto Adjust Algorthirm) | HP Proliant DL360 Gen 9 Server : Direct : | SLES_11_x86_64 | 1. There is an 10mm (approximately ) cut ( Blank Screen ) shown on the top of the screen. 2. Bottom Status Bar is not seen. 3. There is an 10mm (approximately ) cut ( Blank Screen ) shown on the top of the screen. 4. Bottom Status Bar is not seen. |  | P2
10 | 1366x768 75 Hz | Resolution Support and Image adjustment | HP Proliant DL360 Gen 9 Server : Direct : | SLES_11_x86_64 | 1. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. There is an 5mm (approximately ) cut ( Blank Screen ) shown on the right side. 3. LCD8500 OSD displays “1024x768 60 Hz” instead of “1366x768 75 Hz “. 4. Autoconfiguration does not align it. 5. 1366x768 60 Hz works fine. |  | P2
11 | 1024x768 60 Hz | Resolution Support | HP Proliant DL360 Gen 9 Server : Raven / Redbird : | SLES_11_x86_64 | 1. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. 1024x768 75 Hz works fine. | See issue 3, its repeated | P1
12 | 1024x768 60 Hz | Resolution Support | HP Proliant DL380 & DL360 Gen 9 Server : Raven / Redbird / Direct : | SLES_12_x86_64 | 1. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. LCD8500 OSD displays “1024x768 60 Hz”. This is an supported resolution. | See issue 11 | P1
13 | 1024x768 60 Hz | Resolution Support | HP Proliant DL380 and DL360 Gen 9 Server : Raven / Redbird : | SLES_12_x86_64 | 1. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. Direct Connection with the server has no issues with 1024x768 60 Hz. Note: (: Login Screen ) | See issue 11 | P1
14 | 1280x800 60 Hz | Resolution Support | HP Proliant DL380 & DL360 Gen 9 Server : Raven / Redbird / Direct : | SLES_12_x86_64 | 1. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. LCD8500 OSD displays “1024x768 60 Hz” instead of “1280x800 60 Hz “. 3. Bottom Status bar is not visible | Issue is repeated. see 4 | P1
15 | 1440x900 60 Hz | Resolution Support | HP Proliant DL380 and DL360 Gen 9 Server : Raven / Redbird / Direct : | SLES_12_x86_64 | 1. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. LCD8500 OSD displays “1152x870 60 Hz” instead of “1440x900 60 Hz “. 3. Bottom Status bar is not visible | Repeated, issue 5 | P1
16 | 1024x768 60 Hz | Resolution Support | HP Proliant ML350 Gen 8 Server : Redbird : | SLES_12_x86_64 | 1. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. LCD8500 OSD displays “1024x768 60 Hz”. This is an supported resolution. Note : During Installation & Login Screen | See issue 11 | P1
17 | 1024x768 60 Hz | Resolution Support | HP Proliant ML350 Gen 8 Server : Redbird / Raven : | SLES_12_x86_64 | 1. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. LCD8500 OSD displays “1024x768 60 Hz”. This is an supported resolution | Similar to 11, but platform is different, ML350 | P1
18 | 1440x900 60 Hz | Resolution Support | HP Proliant ML350 Gen 8 Server : Direct : | SLES_12_x86_64 | 1. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. LCD8500 OSD displays “1152x870 60 Hz” instead of “1440x900 60 Hz “. 3. Bottom Status bar is not visible. | Similar to 15, platform is different ML350 | P1
19 | 1280x800 60 Hz | Resolution Support | HP Proliant ML350 Gen 8 Server : Direct : | SLES_12_x86_64 | 1. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. LCD8500 OSD displays “1024x768 60 Hz” instead of “1280x800 60 Hz “. 3. Bottom Status bar is not visible. | Similar to 14, diff in platform ML350 | P1
20 | 1024x768 60 Hz | Resolution Support | HP Proliant ML350 Gen 8 Server : Direct : | RHEL_7.2_x86_64 | 1. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. LCD8500 OSD displays “1024x768 60 Hz”. This is a supported resolution Note: Login Screen | OS is different, check issue 17 | P1
21 | 1024x768 60 Hz | Image Adjustment(Auto Adjust Algorthirm) | HP Proliant ML350 Gen 8 Server : Direct : | RHEL_7.2_x86_64 | 1. There is a cut in the Top and Right side of the screen. 2. This issue is intermittent. 3. Autoconfiguration does not fix the issue. | Conflict with issue 20 | P2
22 | 1280x800 60 Hz | Resolution Support | HP Proliant ML350 Gen 8 Server : Direct / Blackbird / Raven : | RHEL_7.2_x86_64 | 1. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. LCD8500 OSD displays “1024x768 60 Hz” instead of “1280x800 60 Hz “. 3. Bottom Status bar is not visible. | OS is different, check issue 19 | P1
23 | 1440x900 60 Hz | Resolution Support | HP Proliant ML350 Gen 8 Server : Direct / Blackbird / Raven : | RHEL_7.2_x86_64 | 1. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. LCD8500 OSD displays “1152x870 60 Hz” instead of “1440x900 60 Hz “. 3. Bottom Status bar is not visible. |  | P1
24 | 1024x768 60 Hz | Resolution Support | HP Proliant ML350 Gen 8 Server : Blackbird / Raven | RHEL_7.2_x86_64 | 1. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ |  | P1
25 | 1366x768 60 Hz | EDID | HP Proliant DL380 Gen 9 Server : Direct : | RHEL_7.1_x86_64 | 1. Distorted Image or Slant Image. 2. This is Known Issue. Fix already discussed with HP. Need to modify the EDID . Note: : Installation / Login Screen / |  | P4
26 | 1024x768 60 Hz | Resolution Support | HP Proliant DL380 Gen 9 Server : Blackbird / Raven : | RHEL_7.1_x86_64 | 4. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 5. LCD8500 OSD displays “1024x768 60 Hz”. This is a supported resolution. Note: : Installation & Login Screen |  | P1
27 | 1024x768 60 Hz | Resolution Support | HP Proliant DL380 Gen 9 Server : Blackbird / Raven / Direct | RHEL_7.1_x86_64 | 1. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. LCD8500 OSD displays “1024x768 60 Hz”. |  | P1
28 | 1280x800 60 Hz | Resolution Support | HP Proliant DL380 Gen 9 Server : Blackbird / Raven / Direct : | RHEL_7.1_x86_64 | 1. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. LCD8500 OSD displays “1024x768 60 Hz” instead of “1280x800 60 Hz “. 3. Bottom Status bar is not visible |  | P1
29 | 1440x900 60 Hz | Resolution Support | HP Proliant DL380 Gen 9 Server : Blackbird / Raven / Direct : | RHEL_7.1_x86_64 | 1. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. LCD8500 OSD displays “1152x870 60 Hz” instead of “1440x900 60 Hz “. 3. Bottom Status bar is not visible. |  | P1
30 | 1366x768 75 Hz | Resolution Support/EDID | HP Proliant DL380 Gen 9 Server : Direct : | RHEL_5.8_x86_64 | 1. Displays Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. LCD8500 OSD displays “1024x768 75 Hz” instead of “1366x768 75 Hz “. 3. 1366x768 60 Hz works fine |  | P3
31 | 800x600 / 1024x768 / 1280x1024 / 1600x1200 / 1680x1050 : 58 Hz | Resolution Support | HP Proliant SL4540 Gen 8 Server : Direct / Raven : | SLES_10_SP4_x86_64 | : All these are supported resolution at either 60 Hz or 75 Hz. But this OS only shows 58 Hz which is not supported. 1. Sometimes these resolutions displays a Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. If the frequency is either 60 or 75 Hz this will be a non-issue. This issue cannot be fixed. A correct display driver which brings up 60 or 75 Hz will not show this issue. |  | P3
32 | 1280x1024 : 58 Hz | Resolution Support | HP Proliant SL4540 Gen 8 Server : Direct / Raven : | SLES_10_SP4_x86_64 | This is a supported resolution at either 60 Hz or 75 Hz. But this OS only shows 58 Hz which is not supported. 1. Sometimes this resolutions displays a Warning Message : “ Current Resolution is not supported , Reverting to best display setting. “ 2. LCD8500 OSD displays “1680x1050” instead of “1280x1024 “. 3. There is a cut at the bottom of the screen. Autoconfiguration does not help. Direct Connection does not show this cut at the bottom. |  | P2

## requirments
| Sub-Task | Estimation/person (days) | Comment | Risk
Pre-requisit
Development Environment setup(Compilation,flash and test) | -Procure compiler -flash tool(ISP,Gprobe) -debug tools(Gprobe,UART) -test the target with hex build locally | 5 | Compiler used by customer is not know. Need to find a suitable compiler. Linker/loader script for target to be defined | High
Understand code flow | source code,library and dependent document reading and make file to be identfied and understand the memory map of the system -Compilation flag identification | 5 | makefile to traced.gsel may be required for auto adjust related issue.Need to check customer do they have gsel library code. | High
Requirment/Task
VGA input detection and display(32 Bug fix, 15 on Redhat and 15 with SUSE,1 Window and 1 unknow) a. Duplicate the issue b. Root cause analysis c. Implement and test d. Release | -Duplicate the issue -document the root cause -trace the code to fix -test | 40 | 15 issues on each platform and one on window. There is similarity in the issue with reference to VGA timing. If some hardware limitation or any library dependene than things may vary. | Moderate
Right now we are using one panel , and the F/W is compatible. We want the same F/W to work with other panels as well , in case we want to change panel later. | -Configuration based multiple panel support. Need to edit PanelArray in panel.c file according to panel spec -test | 2 | Per panel basis. Panel to be received along with cabling compatable with board. | Moderate
Is it possible for the F/W to check the EDID checksum ( or some other data in the EDID ) and pop up a message that “ The current F/W is not compatible to the EDID you have on the board” , Either revert back to the Original F/W or update the EDID “ | -Read EDID data from eprom -check for checksum -revert new firmware(need to see how run time we can do it) -flash edid(need to see from where edid data to be loaded) -test | 10 | Update firmware dynamically need to understand. edid data place holder has to be identfied and loaded to EEPROM | Moderate

## deliverables
Phase | Milestone id | Task | Deliverable | Tentative Date | Comment | Status
First | M0 | Test build with just version no changed | STDP602x.bin | June 8th | Dependent of development tool chain | Close
|  | Environment setup |  | June 30th | Dependent on shipment | Open
project key-off |  |  |  | project key-off
| M1 | Patch for first 5 issue related to Redhat server | STDP602x.bin | July 8th | Dependent of test environment and project key-off
| M2 | Patch for first 10 issue related to Redhat server | STDP602x.bin | July 22nd | Dependent of test environment
| M3 | Patch for first 5 issue related to SUSE server | STDP602x.bin | Aug 5th | Dependent of test environment
| M4 | Patch for first 10 issue related to SUSE server | STDP602x.bin | Aug 19th | Dependent of test environment
| M6 | Source code return | Source code | Aug 26th | Code will be in sync with customer
Second
| M6 | Additional panel support | STDP602x.bin | Sep 9th | Need panel and all dependence
Third | M7 | EDID based firware update | STDP602x.bin | Oct 7th | Enhancement to have EDID read and firmware update logic

## Sheet7
Global State Indicators | Function | Present in File | Explanation
char ROM* ROM szMHStateLabels[] | ---- | modehandler.c | This array contains different states such as stable, unstable, turn to stable, turn to unstable, Init, Open, Close,Out of range
gmt_InputPortArrayType ROM InputPortArray[] |  | modehandler.c | This array has information on IP type, Component, AFR, Skip Scan, Stability check time with sync, Stability hold time with sync, Ptr to array of Standard mode table,Estimated Mode Table

## ArunPrasad_TS
SL No | Planned Task | Estimated(Days) | Actual(days) | Start Date | End Date | Actual Start Date | Actual End Date | % of completion | Status | Comments
1 | Understanding and going through related technical documents | 5 |  | 17/6/2016 |  |  |  | 25% | Progress | Couldn't link the project properly using other compilers. Able to navigate and view different files.

## ArunKS_TS
SL No | Planned Task | Estimated(Days) | Actual(days) | Start Date | End Date | Actual Start Date | Actual End Date | % of completion | Status | Comments
1 | -UPG project overview and discussion | 2 | 2 | 2016-02-06 | 3/6/2016 - | 2016-02-06 | 3/6/2016 - | 100% | Close | Had brief overview and had teleconf with customer team and understand present status of the project
2 | -Project proposal and discussion | 3 | 3 | 2016-02-06 | 2016-08-06 | 2016-02-06 | 2016-08-06 | 100% | Close | Documentation and review
3 | -UPG Monitor Code compilation | 2 | 3 | 2016-06-06 | 2016-07-06 | 2016-06-06 | 2016-08-06 | 100% | Close | Paradigm compiler fetch and Code base used is 1.5 + Genfile from 1.6. Release version 1.7 for test and trial purpose.
4 | Code walk and documenting the design specific to issues | 15 |  | 2016-08-06 | 2016-05-07 | 2016-08-06 |  | 20% | Open | Code walk through to understand the design of firmware
5 | Mentoring coworker | 4 |  | 21/6/2016 | 27/6/2016 | 21/6/2016 |  | 30% | Open | KT with coworker towards project.
6 | - Applying for US-VISA | 4 |  | 14/6/2016 | 20/7/2016 | 14/6/2016 |  | 50% | Open | Chennai travel on 19th and 20th.
7 | Test Environment setup with local code build | 5 | [5 empty] | 0% | Open | Get the equipment from customer and setup the test environment